PMO Architect - User Manual

PMOMax by Katalyst Street

Generated: November 25, 2025

Table of Contents

# PMO Architect - User Manual

## Welcome to PMO Architect

PMO Architect is your comprehensive solution for creating professional Project Initiation Documents (PIDs). This manual will guide you through every feature and capability of the application with step-by-step instructions.

## Table of Contents

- [Getting Started](#getting-started)

- [Understanding the Interface](#understanding-the-interface)

- [Creating Your First PID](#creating-your-first-pid)

- [Section-by-Section Guide](#section-by-section-guide)

- [Working with Tables](#working-with-tables)

- [Using Gantt Charts](#using-gantt-charts)

- [AI Assistant](#ai-assistant)

- [Exporting Your Work](#exporting-your-work)

- [Data Management](#data-management)

- [Tips & Best Practices](#tips--best-practices)

- [Troubleshooting](#troubleshooting)

## Getting Started

### System Requirements

- **Browser**: Chrome 90+, Firefox 88+, Safari 14+, Edge 90+

- **Screen Resolution**: Minimum 1280x720 (1920x1080 recommended)

- **Internet**: Required for initial load, optional thereafter

- **Storage**: At least 10MB available in browser storage

### First Launch

- Open your browser and navigate to the PMO Architect URL

- The application loads automatically - no login required for local mode

- You'll see the welcome screen with quick start options

- Click "Start New Project" or press `Escape` to begin

### Quick Tour

When you first open PMO Architect, you'll see three main areas:

- **Left Sidebar**: Navigation and notes

- **Center Panel**: Input forms for your project data

- **Right Panel**: Live preview of your document

## Understanding the Interface

### Header Bar

Located at the top of the screen, the header contains:

- **Logo**: Returns to home/overview

- **Project Title**: Displays current project name

- **Progress Indicator**: Shows overall completion percentage

- **Help Button** (`?` icon): Opens this manual

- **Settings** (gear icon): Access preferences

### Left Sidebar

#### Navigation Panel

- **7 Section Tabs**: Click to navigate between PID sections

- **Section Icons**: Visual indicators for each section

- **Progress Dots**: Green = complete, Yellow = partial, Gray = empty

- **Collapse Button**: Hide/show sidebar for more space

#### General Notes

- Quick notepad for project ideas

- Auto-saved with your project

- Markdown formatting supported

- Click "General Notes" to expand

#### Table of Contents

- Shows all sections with completion status

- Click any section to jump directly

- Real-time updates as you work

### Main Content Area

#### Input Panel (Left Side)

- **Section Header**: Current section name and description

- **Form Fields**: Input areas for your project data

- **Tables**: For structured data (deliverables, risks, etc.)

- **Charts**: Visual representations (Gantt charts, diagrams)

- **Action Buttons**: Save, Clear, Reset options

#### Output Panel (Right Side)

- **Live Preview**: Real-time document rendering

- **Export Controls**: PDF, Word, JSON download buttons

- **View Options**: Toggle different preview modes

- **Print Button**: Direct browser print functionality

### AI Assistant Panel

- **Toggle Button** (robot icon): Show/hide assistant

- **Chat Interface**: Ask questions, get suggestions

- **Context Awareness**: Knows which section you're working on

- **Suggestion Cards**: Click to apply AI recommendations

## Creating Your First PID

### Step 1: Start a New Project

- Click "Start New Project" on the welcome screen

- Or press `Ctrl/Cmd + N` from anywhere

- Choose "Blank Project" or select a template

### Step 2: Enter Basic Information

- Navigate to **Section 1: Project Overview**

- Fill in the **Project Title** field

- Add a brief **Project Description**

- Click "Save" or wait for auto-save (2 seconds)

### Step 3: Complete Each Section

Work through sections 1-7 in order:

- **Section 1**: Project Overview

- **Section 2**: Scope & Deliverables

- **Section 3**: Schedule & Milestones

- **Section 4**: Resources & Budget

- **Section 5**: Risk Management

- **Section 6**: Communication Plan

- **Section 7**: Quality & Change Control

### Step 4: Review and Export

- Check the progress indicator (aim for 100%)

- Review the live preview in the Output Panel

- Click "Export as PDF" to generate your document

- Download and share with stakeholders

## Section-by-Section Guide

### Section 1: Project Overview

Purpose: Define the project at a high level and establish its foundation.

#### Project Title

- **What to Enter**: A clear, concise name for your project

- **Best Practice**: Use 3-7 words that describe the project

- **Example**: "Customer Portal Modernization Project"

Steps:

- Click into the "Project Title" field

- Type your project name

- Press Tab to move to the next field

#### Project Description

- **What to Enter**: 2-3 paragraphs explaining what the project is

- **Include**: What, Why, and high-level How

- **Example**:

This project aims to modernize our customer-facing web portal
  to improve user experience and increase engagement. The current
  system is outdated and no longer meets customer expectations...

Steps:

- Click into "Project Description"

- Write a comprehensive overview

- Use the AI assistant for suggestions (click the robot icon)

- Review in the Output Panel

#### Project Objectives

- **What to Enter**: Specific, measurable goals

- **Format**: Bullet points or numbered list

- **Best Practice**: Follow SMART criteria (Specific, Measurable, Achievable, Relevant, Time-bound)

Example:

1. Improve page load times by 50%
2. Increase user satisfaction scores from 3.2 to 4.5
3. Reduce customer support tickets by 30%
4. Achieve 99.9% uptime

Steps:

- Click "Project Objectives" field

- List 3-7 key objectives

- Use numbering for clarity

- Ensure each objective is measurable

#### Business Case

- **What to Enter**: Justification for the project

- **Include**:

- Current situation (problem)

- Desired outcome (solution)

- Expected benefits

- Cost/benefit analysis

Template:

Current Situation: [Describe the problem or opportunity]
Proposed Solution: [Explain your approach]
Expected Benefits: [List quantifiable benefits]
Investment Required: [High-level cost estimate]
ROI: [Expected return on investment]

Steps:

- Click "Business Case" field

- Follow the template structure

- Include specific numbers and metrics

- Get stakeholder input before finalizing

#### Key Stakeholders

- **What to Enter**: List of people/groups involved or impacted

- **Format**: Name, Role, Interest level

Example:

- Jane Smith, Executive Sponsor (High interest, High influence)
- IT Department (Medium interest, High influence)
- Customer Service Team (High interest, Medium influence)
- External Customers (High interest, Low influence)

Steps:

- Click "Key Stakeholders" field

- List each stakeholder group

- Note their role and interest/influence level

- Use this as a basis for Section 6 (Communication Plan)

### Section 2: Scope & Deliverables

Purpose: Define what is (and isn't) included in the project.

#### In Scope

- **What to Enter**: Everything the project will deliver

- **Be Specific**: List features, capabilities, locations, timeframes

- **Example**:

- Redesign of main customer portal pages
  - Mobile-responsive layout
  - Integration with CRM system
  - User authentication improvements
  - Training for customer service team
  - Documentation and user guides

Steps:

- Navigate to Section 2

- Click "In Scope" field

- List all deliverables and work included

- Be as specific as possible

#### Out of Scope

- **What to Enter**: What the project will NOT include

- **Purpose**: Prevent scope creep and set expectations

- **Example**:

- Backend system replacement (separate project)
  - Mobile app development
  - Changes to billing system
  - Third-party integrations beyond CRM
  - Custom reporting features

Steps:

- Click "Out of Scope" field

- List exclusions clearly

- Include items stakeholders might expect

- Reference these during scope change discussions

#### Deliverables Table

The Deliverables table tracks specific outputs with details.

Adding a Deliverable:

- Click "Add Deliverable" button

- Fill in the fields:

- Name: What is being delivered

- Description: Details about the deliverable

- Due Date: Target completion date

- Owner: Person/team responsible

- Status: Current state

Example Entry:

Name: Updated Homepage Design
Description: New responsive design for the portal homepage
Due Date: 2025-03-15
Owner: UX Team
Status: In Progress

Managing Deliverables:

- **Edit**: Click the pencil icon on any row

- **Delete**: Click the trash icon

- **Sort**: Click column headers to sort

- **Export**: Click "Export Table" to download as CSV

Steps:

- Click "Add Deliverable"

- Enter all required information

- Set a realistic due date

- Assign an owner

- Update status as work progresses

- Repeat for each major deliverable (typically 5-15 items)

#### Acceptance Criteria

- **What to Enter**: How you'll know deliverables are complete

- **Format**: Specific, testable conditions

- **Example**:

Each deliverable must:
  - Pass all functional tests
  - Meet performance benchmarks
  - Be approved by project sponsor
  - Include complete documentation
  - Pass security review
  - Be deployed to production successfully

Steps:

- Click "Acceptance Criteria" field

- List measurable conditions

- Make criteria binary (yes/no answers)

- Align with stakeholder expectations

### Section 3: Schedule & Milestones

Purpose: Define the project timeline and key dates.

#### Project Timeline

- **What to Enter**: Overall project duration and phases

- **Include**: Start date, end date, major phases

- **Example**:

Project Duration: January 1, 2025 - December 31, 2025
  Phase 1: Planning & Design (Q1 2025)
  Phase 2: Development (Q2-Q3 2025)
  Phase 3: Testing (Q4 2025)
  Phase 4: Deployment (December 2025)

Steps:

- Navigate to Section 3

- Click "Project Timeline" field

- Enter start and end dates

- Break into logical phases

- Allow buffer time for each phase

#### Milestones Table

Milestones are significant points or events in the project.

Adding a Milestone:

- Click "Add Milestone" button

- Fill in:

- Name: Milestone description

- Date: Target date

- Description: What happens at this milestone

- Dependencies: What must complete first

- Status: Current state

Example Milestones:

1. Design Approval - March 15, 2025
2. Development Complete - August 30, 2025
3. User Acceptance Testing Complete - November 15, 2025
4. Go-Live - December 15, 2025

Best Practices:

- Have 5-10 major milestones

- Space them throughout the project

- Make them measurable events

- Include approval/decision points

Steps:

- Click "Add Milestone"

- Enter milestone name

- Set target date

- Add detailed description

- Note any dependencies

- Update status regularly

#### Critical Path

- **What to Enter**: The sequence of tasks that determines project duration

- **Purpose**: Identify where delays have maximum impact

- **Example**:

Critical Path:
  Requirements → Design → Development → Testing → Deployment
  Any delay in these activities will delay the project end date.
  Non-critical activities (parallel work):
  - Documentation (can happen alongside development)
  - Training material creation (can happen during testing)

Steps:

- Click "Critical Path" field

- List the main sequence of dependent activities

- Note which activities are on the critical path

- Identify parallel activities that aren't critical

#### Gantt Chart

The Gantt chart provides visual timeline representation.

Creating Your Gantt Chart:

- **Add a Phase**:

- Click "Add Phase" button

- Enter phase name (e.g., "Design")

- Set start date

- Set end date

- Choose a color

- Set progress percentage

- **Add Tasks to Phase**:

- Click on a phase to expand it

- Click "Add Task"

- Enter task details:

- Name

- Start/end dates

- Assignee

- Progress

- Dependencies

- **View Options**:

- High-Level View: Shows only phases

- Detailed View: Shows all tasks

- Resource View: Groups by assignee

- Milestone View: Highlights key dates

- **Editing**:

- Drag phase bars to adjust dates

- Click phase/task to edit details

- Set dependencies by clicking and dragging

- Update progress by clicking the progress bar

Example Gantt Structure:

Phase 1: Planning (Jan 1 - Mar 31)
├── Task: Requirements Gathering (Jan 1 - Jan 31)
├── Task: Stakeholder Interviews (Feb 1 - Feb 15)
└── Task: Design Specifications (Feb 16 - Mar 31)
Phase 2: Development (Apr 1 - Aug 31)
├── Task: Backend Development (Apr 1 - Jun 30)
├── Task: Frontend Development (May 1 - Aug 15)
└── Task: Integration (Aug 1 - Aug 31)

Steps:

- Start with high-level phases

- Add 3-7 major phases

- Break each phase into tasks (3-10 tasks per phase)

- Set realistic durations

- Note dependencies

- Assign resources

- Update progress weekly

Tips:

- Use different colors for different phase types

- Keep task names short (3-5 words)

- Update progress regularly (weekly)

- Show the Gantt chart in stakeholder meetings

### Section 4: Resources & Budget

Purpose: Define who will work on the project and how much it will cost.

#### Team Structure

- **What to Enter**: Organization of the project team

- **Include**: Roles, reporting lines, responsibilities

- **Example**:

Project Manager: Jane Doe
  └── Technical Lead: John Smith
      ├── Senior Developer (2)
      ├── Junior Developer (3)
      └── QA Engineer (2)
  └── UX Lead: Sarah Johnson
      ├── UX Designer (1)
      └── UI Designer (1)
  └── Business Analyst: Mike Chen
  Supporting Roles:
  - Executive Sponsor: VP of IT
  - Product Owner: Director of Customer Experience
  - Stakeholder Committee: Monthly oversight

Steps:

- Navigate to Section 4

- Click "Team Structure" field

- List all roles in hierarchical format

- Include full-time and part-time resources

- Note reporting relationships

#### Resource Allocation Table

Track specific resources and their allocation to the project.

Adding a Resource:

- Click "Add Resource" button

- Fill in details:

- Name: Person's name

- Role: Their position/function

- Allocation: Percentage (0-100%)

- Start Date: When they join

- End Date: When they finish

- Cost: Rate per period

- Period: Hourly/Daily/Monthly

Example Resources:

| Name | Role | Allocation | Start | End | Cost | Period |
|------|------|------------|-------|-----|------|--------|
| John Smith | Tech Lead | 100% | 2025-01-01 | 2025-12-31 | $75 | hourly |
| Jane Wilson | Developer | 50% | 2025-03-01 | 2025-09-30 | $60 | hourly |
| Bob Jones | QA Engineer | 100% | 2025-08-01 | 2025-12-31 | $55 | hourly |

Steps:

- Click "Add Resource"

- Enter each team member

- Set realistic allocation percentages

- Include contractors and vendors

- Update as resources change

Calculating Resource Costs:

- 100% allocation = full-time

- 50% allocation = half-time

- Multiply: hours × rate × allocation × duration

#### Budget Breakdown Table

Track all project costs by category.

Adding a Budget Item:

- Click "Add Budget Item"

- Select **Category**:

- Personnel

- Equipment

- Software

- Training

- Travel

- Consulting

- Contingency

- Other

- Enter:

- Item: Specific description

- Planned: Budgeted amount

- Actual: Spent to date

- Variance: Calculated automatically

- Notes: Additional context

Example Budget:

| Category | Item | Planned | Actual | Variance | Notes |
|----------|------|---------|--------|----------|-------|
| Personnel | Development Team | $500,000 | $475,000 | -$25,000 | Under budget |
| Software | Licenses | $50,000 | $52,000 | +$2,000 | Additional tools |
| Equipment | Servers | $100,000 | $0 | $0 | Not purchased yet |
| Contingency | Risk Buffer | $75,000 | $15,000 | -$60,000 | 20% used |

Best Practices:

- Include 10-20% contingency

- Track actuals monthly

- Update variance regularly

- Flag items >10% over budget

Steps:

- Click "Add Budget Item"

- Enter all cost categories

- Be realistic with planned amounts

- Update actuals monthly

- Review variances in meetings

#### Cost Tracking

- **What to Enter**: How you'll monitor and control costs

- **Include**: Tracking frequency, approval processes, reporting

- **Example**:

Budget Monitoring:
  - Weekly review of actuals vs. planned
  - Monthly financial reports to sponsor
  - Variance analysis for items >5% off plan
  Approval Process:
  - PM approval: Up to $5,000
  - Sponsor approval: $5,000-$25,000
  - Executive committee: >$25,000
  Cost Control Measures:
  - Change request process for scope additions
  - Regular resource utilization reviews
  - Vendor invoice validation
  - Quarterly budget reforecasts

Steps:

- Click "Cost Tracking" field

- Define tracking frequency

- Set approval thresholds

- Document control measures

- Specify reporting format

### Section 5: Risk Management

Purpose: Identify potential problems and plan mitigation strategies.

#### Risk Register Table

The central tool for tracking all project risks.

Adding a Risk:

- Click "Add Risk" button

- Fill in all fields:

- Description: What could go wrong

- Category: Type of risk

- Probability: Likelihood (1-5)

- Impact: Severity if it occurs (1-5)

- Score: Calculated (Probability × Impact)

- Mitigation: How to prevent/reduce

- Owner: Who monitors this risk

- Status: Current state

Risk Categories:

- Technical: Technology challenges

- Resource: People availability

- Schedule: Timeline issues

- Budget: Cost overruns

- Stakeholder: Relationship problems

- External: Outside factors

- Legal: Compliance issues

- Operational: Day-to-day operations

Risk Levels:

- **Probability**:

- 1 = Very Unlikely (< 10%)

- 2 = Unlikely (10-30%)

- 3 = Possible (30-50%)

- 4 = Likely (50-70%)

- 5 = Very Likely (> 70%)

- **Impact**:

- 1 = Negligible (minor inconvenience)

- 2 = Low (small delays/costs)

- 3 = Medium (noticeable impact)

- 4 = High (significant problems)

- 5 = Critical (project failure)

Risk Scoring:

Score = Probability × Impact
1-5: Low Risk (Monitor)
6-10: Medium Risk (Mitigate)
11-15: High Risk (Actively Manage)
16-25: Critical Risk (Immediate Action)

Example Risks:

Risk: Key developer leaves project
Category: Resource
Probability: 3
Impact: 4
Score: 12 (High)
Mitigation: Cross-training, documentation, backup resources
Owner: Project Manager
Status: Monitoring
Risk: Integration with legacy system fails
Category: Technical
Probability: 4
Impact: 5
Score: 20 (Critical)
Mitigation: Early integration testing, technical POC, vendor support
Owner: Technical Lead
Status: Mitigating

Steps:

- Brainstorm risks with team (aim for 10-20 risks)

- Click "Add Risk" for each one

- Rate probability and impact honestly

- Focus on high-score risks first

- Define clear mitigation strategies

- Assign risk owners

- Review and update weekly

#### Risk Matrix

- **What to Enter**: Visual representation of risk distribution

- **Purpose**: Show risk landscape at a glance

- **Automatically Generated**: Based on risk table data

The risk matrix plots all risks:

- **X-axis**: Probability (1-5)

- **Y-axis**: Impact (1-5)

- **Colors**:

- Green: Low risk (1-5)

- Yellow: Medium risk (6-10)

- Orange: High risk (11-15)

- Red: Critical risk (16-25)

Reading the Matrix:

- Upper right: Critical risks (need immediate attention)

- Lower left: Low risks (monitor only)

- Diagonal: Balanced risks (probability = impact)

Steps:

- Add all risks to the Risk Register

- The matrix updates automatically

- Use in meetings to visualize risk status

- Export as image for reports

#### Mitigation Strategies

- **What to Enter**: Overall approach to risk management

- **Include**: Response strategies, escalation, monitoring

- **Example**:

Risk Response Strategies:
  1. Avoid: Change plan to eliminate risk
     - Example: Use proven technology instead of cutting-edge
  2. Mitigate: Reduce probability or impact
     - Example: Add extra testing to reduce defect risk
  3. Transfer: Shift risk to third party
     - Example: Purchase insurance, use vendors with SLAs
  4. Accept: Acknowledge and monitor
     - Example: Low-probability, low-impact risks
  Risk Review Process:
  - Weekly team risk reviews
  - Monthly sponsor risk reports
  - Immediate escalation for critical risks
  - Quarterly risk register refresh
  Contingency Planning:
  - Trigger points for activating contingency plans
  - Pre-approved contingency budget
  - Decision trees for common risk scenarios

Steps:

- Click "Mitigation Strategies" field

- Document overall risk approach

- Define response categories

- Set review frequency

- Create escalation procedures

### Section 6: Communication Plan

Purpose: Define how project information will be shared.

#### Stakeholder Communication Table

Plan communication for each stakeholder group.

Adding a Stakeholder Communication Plan:

- Click "Add Stakeholder"

- Fill in:

- Stakeholder: Name/group

- Role: Their position

- Interest: Low/Medium/High

- Influence: Low/Medium/High

- Method: How to communicate

- Frequency: How often

- Notes: Preferences/requirements

Communication Methods:

- Email: Written updates

- Meeting: Face-to-face or virtual

- Phone: Quick discussions

- Dashboard: Self-service access

- Report: Formal documentation

- Presentation: Formal briefings

- Slack/Teams: Instant messaging

Communication Frequency:

- Daily: Critical team members

- Weekly: Core team

- Bi-weekly: Extended team

- Monthly: Management/sponsors

- Quarterly: Executive level

- As Needed: Ad-hoc stakeholders

- Milestone-based: Key decision points

Example Stakeholder Communications:

| Stakeholder | Role | Interest | Influence | Method | Frequency | Notes |
|-------------|------|----------|-----------|--------|-----------|-------|
| Executive Sponsor | VP IT | High | High | Presentation | Monthly | Prefers executive summary |
| Project Team | Core Team | High | Medium | Meeting | Weekly | Stand-ups + Slack |
| End Users | Customers | High | Low | Email | Monthly | Newsletter format |
| IT Operations | Support | Medium | High | Meeting | Bi-weekly | Technical details needed |

Interest/Influence Matrix:

- **High Interest, High Influence**: Manage closely

- **High Interest, Low Influence**: Keep informed

- **Low Interest, High Influence**: Keep satisfied

- **Low Interest, Low Influence**: Monitor only

Steps:

- List all stakeholder groups

- Click "Add Stakeholder" for each

- Assess interest and influence honestly

- Match communication method to preferences

- Set appropriate frequency

- Document special requirements

#### Meeting Schedule

- **What to Enter**: Recurring meeting cadence

- **Include**: Meeting types, frequency, attendees, agenda

- **Example**:

Daily Stand-up (15 min)
  - Time: 9:00 AM daily
  - Attendees: Core project team
  - Format: Quick status updates (what done, what next, blockers)
  Weekly Status Meeting (60 min)
  - Time: Fridays 2:00 PM
  - Attendees: Project team + key stakeholders
  - Agenda: Progress review, risk discussion, decision making
  Monthly Steering Committee (90 min)
  - Time: First Monday of month, 10:00 AM
  - Attendees: Sponsor, PM, stakeholder representatives
  - Agenda: Strategic review, budget approval, major decisions
  Quarterly Executive Review (30 min)
  - Time: End of quarter
  - Attendees: Executive team, sponsor, PM
  - Format: High-level presentation with Q&A

Steps:

- Click "Meeting Schedule" field

- Define each recurring meeting

- Include timing, attendees, purpose

- Set up calendar invites

- Document agenda templates

#### Reporting Structure

- **What to Enter**: How project status is reported

- **Include**: Report types, content, distribution

- **Example**:

Weekly Status Report:
  - Format: Email summary
  - Content: Progress, issues, decisions needed
  - Distribution: Core team, sponsor
  - Due: Friday 5:00 PM
  Monthly Dashboard:
  - Format: PowerPoint/PDF
  - Content: Metrics, budget, schedule, risks
  - Distribution: Steering committee
  - Due: 3 days before monthly meeting
  Milestone Reports:
  - Format: Formal document
  - Content: Achievement summary, lessons learned, next steps
  - Distribution: All stakeholders
  - Timing: Within 3 days of milestone completion
  Issue/Risk Escalations:
  - Format: Email + meeting request
  - Content: Issue description, impact, recommended action
  - Distribution: Based on escalation level
  - Timing: Immediate for critical items

Steps:

- Click "Reporting Structure" field

- Define each report type

- Specify format and content

- Set distribution lists

- Document timing/frequency

### Section 7: Quality & Change Control

Purpose: Ensure deliverables meet standards and manage changes properly.

#### Quality Assurance

- **What to Enter**: How quality will be ensured

- **Include**: Standards, processes, checkpoints

- **Example**:

Quality Standards:
  - Code Review: All code peer-reviewed before merge
  - Testing: 80% code coverage minimum
  - Documentation: All features documented
  - Performance: Page load < 2 seconds
  - Security: OWASP Top 10 compliance
  - Accessibility: WCAG 2.1 AA compliant
  Quality Processes:
  1. Requirements Review
     - All requirements reviewed by stakeholders
     - Sign-off before development starts
  2. Design Review
     - Technical design peer-reviewed
     - Architecture approval by tech lead
  3. Code Quality
     - Automated linting and formatting
     - Unit test requirements
     - Code review checklist
  4. Testing Phases
     - Unit testing (developers)
     - Integration testing (QA team)
     - User acceptance testing (business)
     - Performance testing (DevOps)
  Quality Checkpoints:
  - End of each sprint: Demo + retrospective
  - End of each phase: Formal quality review
  - Before release: Go/no-go decision meeting

Steps:

- Navigate to Section 7

- Click "Quality Assurance" field

- Define quality standards

- Document QA processes

- Set review checkpoints

#### Testing Procedures

- **What to Enter**: Specific testing approach

- **Include**: Test types, responsibilities, success criteria

- **Example**:

Test Strategy:
  Unit Testing:
  - Responsibility: Developers
  - Coverage: 80% minimum
  - Tools: Jest, React Testing Library
  - Timing: Before code merge
  Integration Testing:
  - Responsibility: QA Team
  - Scope: API endpoints, system interfaces
  - Tools: Postman, automated scripts
  - Timing: After each integration
  System Testing:
  - Responsibility: QA Team
  - Scope: End-to-end workflows
  - Tools: Selenium, Cypress
  - Timing: End of development phase
  User Acceptance Testing (UAT):
  - Responsibility: Business users
  - Scope: Real-world scenarios
  - Format: Guided test scripts
  - Timing: 2 weeks before go-live
  - Success Criteria: 95% test cases pass
  Performance Testing:
  - Responsibility: DevOps team
  - Metrics: Response time, throughput, resource usage
  - Tools: JMeter, LoadRunner
  - Acceptance: Response time < 2s for 95th percentile
  Security Testing:
  - Responsibility: Security team
  - Scope: Vulnerability scan, penetration test
  - Tools: OWASP ZAP, Nessus
  - Timing: Before production deployment
  Regression Testing:
  - Responsibility: QA Team
  - Scope: Existing functionality
  - Frequency: Before each release
  - Automation: 70% automated
  Defect Management:
  - Severity Levels: Critical, High, Medium, Low
  - Response Times: Critical (4 hrs), High (1 day), Medium (3 days), Low (1 week)
  - Tracking Tool: Jira
  - Review: Daily defect triage meetings

Steps:

- Click "Testing Procedures" field

- Define all test types

- Assign responsibilities

- Set success criteria

- Document defect process

#### Change Control

- **What to Enter**: How changes to scope/schedule/budget are managed

- **Include**: Process, approval levels, documentation

- **Example**:

Change Request Process:
  1. Change Identification
     - Any team member can identify a needed change
     - Document in change request form
  2. Change Request Form
     Required Information:
     - Description of change
     - Reason/justification
     - Impact on scope/schedule/budget
     - Affected deliverables
     - Alternatives considered
     - Recommended action
  3. Impact Analysis
     - Project Manager assesses impact
     - Consults with technical lead, stakeholders
     - Documents risks and implications
     - Estimates cost and timeline impact
  4. Approval Workflow
     - Minor changes (< 40 hours, no budget impact): PM approval
     - Medium changes (< $10k, < 2 week delay): Sponsor approval
     - Major changes (>$10k or > 2 week delay): Steering committee
     - Scope changes: Always require sponsor approval
  5. Implementation
     - Update project plan
     - Communicate to all stakeholders
     - Track in change log
     - Update relevant documents
  6. Review
     - Monthly change summary to steering committee
     - Trend analysis (too many changes = problem)
  Change Control Board:
  - Members: Sponsor, PM, Tech Lead, Business Owner
  - Meeting: Weekly (or as needed for urgent changes)
  - Quorum: 3 of 4 members
  - Decision: Approve, Reject, or Request More Info
  Emergency Changes:
  - Critical defects or security issues
  - PM can approve immediately
  - Retroactive CCB review within 24 hours

Steps:

- Click "Change Control" field

- Define change request process

- Set approval thresholds

- Document Change Control Board

- Create change request template

#### Version Control

- **What to Enter**: How document and code versions are managed

- **Include**: Naming conventions, tools, responsibilities

- **Example**:

Document Version Control:
  Naming Convention:
  [DocumentName]_v[Major].[Minor]_[Date]_[Status]
  Example: PID_v1.2_20251125_DRAFT
  Version Numbering:
  - Major version (1.x): Significant changes, stakeholder approval required
  - Minor version (x.1): Small updates, content changes
  - Date: YYYYMMDD format
  - Status: DRAFT, REVIEW, APPROVED, FINAL
  Document Repository:
  - Location: SharePoint/Google Drive
  - Structure: /Project/Documents/[DocumentType]/
  - Access: Read for all, write for PM and designated editors
  - Backups: Automatic daily backups
  Code Version Control:
  Source Control System: Git (GitHub/GitLab)
  Branching Strategy:
  - main: Production code
  - develop: Integration branch
  - feature/*: Feature development
  - hotfix/*: Emergency fixes
  - release/*: Release preparation
  Commit Standards:
  - Meaningful commit messages
  - Reference ticket/issue numbers
  - Sign-off required for main branch
  Release Versioning:
  - Format: v[Major].[Minor].[Patch]
  - Example: v1.2.3
  - Major: Breaking changes
  - Minor: New features (backward compatible)
  - Patch: Bug fixes
  Tagging:
  - Tag all releases in Git
  - Include release notes
  - Sign tags with GPG key
  Version Control Responsibilities:
  - Developers: Commit regularly, follow standards
  - Tech Lead: Code review, merge approval
  - PM: Document versioning, release coordination
  - QA: Test versioned releases

Steps:

- Click "Version Control" field

- Define naming conventions

- Document repository structure

- Set branching strategy (for code)

- Assign responsibilities

## Working with Tables

### Table Features

All tables in PMO Architect have consistent functionality:

#### Adding Rows

- Click "Add [Item]" button at top of table

- Fill in the inline form that appears

- Required fields marked with `*`

- Click "Save" or press `Enter` to add

- Click "Cancel" or press `Escape` to discard

#### Editing Rows

- Click the **pencil icon** (✏️) in the row

- Fields become editable

- Make your changes

- Click "Save" checkmark or press `Enter`

- Click "Cancel" X or press `Escape` to revert

#### Deleting Rows

- Click the **trash icon** (🗑️) in the row

- Confirm deletion in the popup dialog

- Action cannot be undone (unless you restore from backup)

#### Sorting

- Click any column header

- First click: Sort ascending

- Second click: Sort descending

- Third click: Remove sort (return to original order)

- Hold `Shift` and click multiple columns for multi-column sort

#### Filtering

- Click the **filter icon** (🔍) in column header

- Enter search text or select filter values

- Multiple filters combine with AND logic

- Click "Clear Filters" to reset

#### Exporting

- Click "Export Table" button

- Choose format:

- CSV: For Excel, Google Sheets

- JSON: For data backup

- Print: For hard copy

- File downloads automatically

### Table Keyboard Shortcuts

- `Tab`: Move to next field

- `Shift + Tab`: Move to previous field

- `Enter`: Save current edit

- `Escape`: Cancel current edit

- `Delete`: Delete selected row (with confirmation)

- `Ctrl/Cmd + A`: Select all rows

- `Ctrl/Cmd + C`: Copy selected rows

## Using Gantt Charts

### Gantt Chart Basics

The Gantt chart provides visual project timeline management.

#### Chart Elements

- **Phases**: High-level project stages (colored bars)

- **Tasks**: Detailed work items within phases

- **Timeline**: Date scale along the top

- **Dependencies**: Lines connecting related items

- **Progress**: Filled portion of bars shows completion

- **Milestones**: Diamond markers for key dates

#### Adding Phases

- Click "Add Phase" button

- Fill in the form:

- Name: Phase description

- Start Date: When phase begins

- End Date: When phase ends

- Color: Visual identifier (click color picker)

- Progress: Current completion (0-100%)

- Click "Save"

Best Practices:

- Use 3-7 main phases

- Keep phases at similar granularity

- Avoid overlapping phases unless parallel work

- Choose distinct colors for each phase

#### Adding Tasks

- Click on a phase to expand it

- Click "Add Task" button

- Fill in task details:

- Name: Brief task description

- Start Date: Task start

- End Date: Task end

- Assignee: Who's responsible

- Progress: Completion percentage

- Dependencies: Other tasks this depends on

- Click "Save"

Best Practices:

- 3-10 tasks per phase

- Tasks should be 1-4 weeks in duration

- Assign one primary owner per task

- Set realistic durations with buffer

#### Setting Dependencies

Method 1: While Creating/Editing:

- Open task edit form

- In "Dependencies" field, select prerequisite tasks

- Multiple dependencies allowed

- Save task

Method 2: Visual Linking (if enabled):

- Click and hold on task's dependency handle

- Drag to the dependent task

- Release to create link

- Line appears showing dependency

Dependency Types:

- **Finish-to-Start (FS)**: Most common - Task B starts when Task A finishes

- **Start-to-Start (SS)**: Task B starts when Task A starts

- **Finish-to-Finish (FF)**: Task B finishes when Task A finishes

- **Start-to-Finish (SF)**: Rare - Task B finishes when Task A starts

#### Adjusting Dates

Method 1: Drag and Drop:

- Click on phase/task bar

- Drag left/right to change duration

- Drag entire bar to move without changing duration

- Release to save

Method 2: Date Picker:

- Click pencil icon to edit

- Use date picker for precise dates

- Save changes

Date Validation:

- End date must be after start date

- Tasks can't extend beyond phase dates

- Dependent tasks validated against prerequisites

- Warnings shown for conflicts

#### Updating Progress

- Click on phase/task

- Find "Progress" field (0-100%)

- Enter current completion percentage

- Save

Visual Progress:

- Bar fills from left to right

- Different shade shows completed portion

- Percentage displayed on bar

- Update weekly for accuracy

#### View Modes

Click the view mode dropdown to switch views:

High-Level View:

- Shows only phases

- Best for executive presentations

- Clear overview of major milestones

- Ideal for monthly reviews

Detailed View:

- Shows phases and all tasks

- Best for team planning

- Allows detailed tracking

- Use for weekly status meetings

Resource-Focused View:

- Groups tasks by assignee

- Shows workload distribution

- Identifies resource conflicts

- Good for resource planning

Milestone View:

- Emphasizes key dates

- Shows milestones as diamonds

- Phases shown in light background

- Best for stakeholder communications

#### Preset Configurations

PMO Architect includes helpful presets:

- Click "Presets" dropdown

- Select a preset:

- Default: Balanced view

- Executive Summary: High-level only

- Team Planning: Detailed task view

- Resource Planning: Grouped by person

- Customize and save your own presets

#### Exporting Gantt Charts

- Click "Export Gantt" button

- Choose format:

- PNG Image: For presentations

- PDF: For printing

- Excel: For further analysis

- Select date range (optional)

- Include options:

- Show dependencies

- Show progress

- Show assignees

- Color coding

- Click "Download"

#### Tips for Effective Gantt Charts

Planning:

- Start with phases, then add tasks

- Build in buffer time (20% recommended)

- Set conservative estimates

- Consider resource availability

Maintenance:

- Update progress weekly

- Adjust dates as needed

- Document changes in notes

- Review dependencies regularly

Communication:

- Use different views for different audiences

- Export for stakeholder reports

- Highlight critical path

- Show progress visually

Common Mistakes to Avoid:

- Too many tasks (keep it manageable)

- Unrealistic durations

- Missing dependencies

- Forgetting to update progress

- Overlapping resource assignments

## AI Assistant

### Overview

The AI Assistant helps you create content, get suggestions, and improve your PID.

### Accessing the Assistant

- Click the **robot icon** in the bottom-right corner

- Or press `Ctrl/Cmd + /`

- Panel slides in from the right

- Click again to hide

### Using the Assistant

#### Asking Questions

- Type your question in the chat box

- Press `Enter` to send

- AI responds within seconds

- Responses are contextual to current section

Example Questions:

- "What should I include in the business case?"

- "Help me identify risks for a web development project"

- "Suggest milestones for a 6-month project"

- "What acceptance criteria should I define?"

#### Getting Content Suggestions

- Navigate to the section you need help with

- Click "Get Suggestions" button

- AI analyzes your existing content

- Provides relevant additions and improvements

Example Uses:

- Generate risk items based on project type

- Suggest deliverables for common projects

- Create milestone templates

- Draft communication plans

#### Applying Suggestions

- Review AI suggestion

- Click "Apply" to insert into current field

- Or click "Edit" to modify before applying

- Or click "Dismiss" to ignore

Note: Always review and customize AI suggestions. They're starting points, not final content.

#### Context Awareness

The AI knows:

- Which section you're in

- What you've already entered

- Your project type and scope

- Industry best practices

Smart Features:

- Suggestions match your writing style

- Content aligns with previous sections

- Terminology is consistent

- Recommendations are appropriate to project size

### AI Assistant Best Practices

Do:

- Be specific in questions

- Review all suggestions before applying

- Customize AI content for your project

- Use AI for brainstorming and ideas

- Ask follow-up questions

Don't:

- Blindly accept all suggestions

- Share sensitive/confidential info

- Rely solely on AI without review

- Use AI output as final without editing

- Assume AI knows your specific context

### Privacy Note

- AI assistance is optional

- Can be disabled in settings

- Conversations are not stored permanently

- No data shared with third parties

## Exporting Your Work

### Export Options

PMO Architect supports three export formats:

#### PDF Export

When to Use:

- Stakeholder presentations

- Formal documentation

- Print copies

- Email sharing

- Read-only distribution

Steps:

- Click "Export" dropdown in header

- Select "Export as PDF"

- Choose options:

- Include all sections or select specific ones

- Include/exclude table of contents

- Add page numbers

- Include headers/footers

- Click "Generate PDF"

- Wait for processing (10-30 seconds)

- PDF downloads automatically

- Open to verify formatting

PDF Features:

- Professional formatting

- Clickable table of contents

- Page numbers

- Headers with project title

- Footers with date/version

- Preserved colors and styling

Tips:

- Review in preview panel first

- Check all tables render correctly

- Verify Gantt charts are readable

- Test links in TOC

#### Word Export (DOCX)

When to Use:

- Further editing needed

- Template creation

- Collaboration with others

- Custom formatting required

- Merging with other documents

Steps:

- Click "Export" dropdown

- Select "Export as Word"

- Choose sections to include

- Select style options:

- Font family

- Font size

- Heading styles

- Click "Generate DOCX"

- File downloads automatically

- Open in Word/Google Docs

Word Export Features:

- Editable text

- Formatted tables

- Heading hierarchy

- Styles applied

- Compatible with Microsoft Word 2016+

- Works with Google Docs

- Compatible with LibreOffice

Tips:

- Tables may need reformatting

- Images embedded at screen resolution

- Styles can be modified in Word

- Save as template for future use

#### JSON Export

When to Use:

- Data backup

- Version control

- Sharing with others for import

- Migrating to another system

- Data analysis

Steps:

- Click "Export" dropdown

- Select "Export as JSON"

- Optionally minify for smaller file

- Click "Generate JSON"

- File downloads immediately

JSON Features:

- Complete data preservation

- Human-readable format

- Can be imported back

- Includes all metadata

- Version information included

Tips:

- Regular backups recommended

- Store in version control (Git)

- Compress for sharing

- Validate JSON if edited manually

### Import from JSON

Steps:

- Click "Import" in the File menu

- Select "Import from JSON"

- Choose JSON file from computer

- Review data preview

- Choose import option:

- Replace All: Overwrites current data

- Merge: Combines with existing data

- Create New: Starts new project with imported data

- Click "Import"

- Verify data loaded correctly

Important:

- Importing replaces current data (with Replace All option)

- Create backup before importing

- Verify JSON file source

- Check version compatibility

### Print Functionality

Direct Browser Print:

- Click "Print" button or press `Ctrl/Cmd + P`

- Browser print dialog opens

- Choose printer or "Save as PDF"

- Adjust settings:

- Paper size

- Margins

- Orientation

- Click "Print"

Print Optimization:

- Page breaks at section boundaries

- Tables split appropriately

- Gantt charts scaled to fit

- Headers/footers included

## Data Management

### Auto-Save

- Automatically saves every 2 seconds

- Saves to browser's localStorage

- No manual save needed

- Indicator shows "Saved" when complete

If Auto-Save Fails:

- Check browser storage permissions

- Clear browser cache

- Manually export JSON as backup

- Check available storage space

### Manual Save

- Press `Ctrl/Cmd + S`

- Or click "Save" button in header

- Confirmation message appears

- Data persists to localStorage

### Data Persistence

Where Data is Stored:

- Browser's localStorage

- On your computer only

- Not sent to servers

- Persists across sessions

Storage Limits:

- Typically 5-10 MB

- Varies by browser

- Warning shown when approaching limit

### Clearing Data

Clear Current Project:

- Click "File" menu

- Select "Clear Project"

- Confirm in dialog

- All sections reset to empty

- Cannot be undone (export first!)

Reset to Demo Data:

- Click "File" menu

- Select "Load Demo Data"

- Confirm overwrite

- Demo project loads

- Use for learning/testing

### Backup & Recovery

Creating Backups:

- Export as JSON regularly (weekly recommended)

- Name files with dates: `Project_2025-11-25.json`

- Store in cloud storage (Google Drive, Dropbox)

- Keep multiple versions

Restoring from Backup:

- Click "Import" in File menu

- Select backup JSON file

- Review data preview

- Click "Import"

- Verify data restored correctly

Best Practices:

- Backup before major changes

- Keep at least 3 recent backups

- Test restore process

- Store backups in multiple locations

### Data Security

Local Data:

- Never leaves your computer

- Stored in browser only

- Cleared when browser data cleared

- Not accessible to websites/other apps

Exporting Safely:

- Be cautious with sensitive data

- Use encryption for confidential PIDs

- Secure file sharing methods

- Consider password-protected files

## Tips & Best Practices

### Getting Started

- **Start with Section 1**: Build foundation first

- **Use Templates**: Load demo data to see examples

- **One Section at a Time**: Don't jump around randomly

- **Save Often**: Though auto-save works, manual saves don't hurt

- **Ask AI**: Use assistant when stuck

### Writing Content

- **Be Specific**: Avoid vague statements

- **Use Numbers**: Quantify whenever possible

- **Keep it Concise**: Bullet points over paragraphs

- **Think Audience**: Write for stakeholders who will read it

- **Consistency**: Use same terms throughout

### Managing Projects

- **Realistic Estimates**: Better to under-promise and over-deliver

- **Buffer Time**: Add 20% contingency to schedules

- **Identify Risks Early**: Better to plan for problems

- **Regular Updates**: Keep data current (weekly reviews)

- **Stakeholder Engagement**: Involve them throughout

### Using Tables Effectively

- **Keep Tables Focused**: Don't try to track everything

- **Update Regularly**: Stale data is worse than no data

- **Use Status Fields**: Easy way to see what needs attention

- **Assign Owners**: Clear accountability

- **Export for Analysis**: Use Excel for deeper insights

### Gantt Chart Tips

- **Start High-Level**: Add detail gradually

- **Realistic Dependencies**: Don't over-constrain

- **Update Progress Weekly**: Keeps chart relevant

- **Use Colors Meaningfully**: Consistent color coding

- **Show What Matters**: Don't clutter with too much detail

### Collaboration

- **Share Early**: Get feedback on draft PIDs

- **Export PDFs**: Easy for stakeholders to review

- **Version Control**: Use JSON exports in Git

- **Document Changes**: Note what changed in each version

- **Review Together**: Walk through in meetings

### Quality Assurance

- **Peer Review**: Have someone else read it

- **Spell Check**: Run through a grammar checker

- **Check Numbers**: Verify calculations are correct

- **Test Links**: If including URLs, test them

- **Print Preview**: See how it looks on paper

## Troubleshooting

### Common Issues

#### Data Not Saving

Symptoms: Changes disappear after reload

Solutions:

- Check browser console for errors (F12)

- Verify localStorage isn't disabled

- Check available storage space

- Disable browser extensions temporarily

- Try incognito/private mode

- Clear browser cache and reload

- Export JSON as manual backup

#### Export Not Working

Symptoms: PDF/Word doesn't download

Solutions:

- Disable pop-up blocker

- Check browser download permissions

- Try different export format

- Clear browser cache

- Check for browser console errors

- Try different browser

- Ensure all required fields filled

#### Gantt Chart Not Displaying

Symptoms: Blank chart area

Solutions:

- Add at least one phase

- Verify dates are valid format

- Check start date is before end date

- Refresh the page

- Clear chart data and re-enter

- Check browser console for errors

#### Performance Issues

Symptoms: Slow, laggy interface

Solutions:

- Close other browser tabs

- Reduce number of table rows

- Simplify Gantt chart (fewer tasks)

- Close AI assistant if not using

- Clear browser cache

- Update browser to latest version

- Export and reimport data (resets state)

#### AI Assistant Not Responding

Symptoms: No response from AI

Solutions:

- Check internet connection

- Reload the page

- Try simpler question

- Check if AI service is enabled in settings

- Clear browser cache

- Try different browser

#### Import Fails

Symptoms: JSON import doesn't work

Solutions:

- Verify JSON file is valid (use validator)

- Check file wasn't corrupted

- Ensure file is from PMO Architect

- Check version compatibility

- Try opening JSON in text editor

- Re-export from original source

### Error Messages

#### "Storage Quota Exceeded"

Meaning: Browser storage is full

Solutions:

- Export current project

- Clear old projects from storage

- Clear browser data

- Use JSON export for large projects

#### "Invalid Date Format"

Meaning: Date entered incorrectly

Solutions:

- Use date picker instead of typing

- Follow format: YYYY-MM-DD

- Check for typos in dates

- Verify month/day aren't swapped

#### "Validation Error"

Meaning: Required field is empty or invalid

Solutions:

- Check for red field highlights

- Fill in all required fields

- Review error message for specifics

- Check for special character issues

### Getting Help

If you can't resolve an issue:

- **Check Help Modal**: Press `?` or click help icon

- **Review Documentation**: This manual and data structure guide

- **Search GitHub Issues**: May be a known issue

- **Report Bug**: Create GitHub issue with details

- **Contact Support**: Email with screenshots and description

When Reporting Issues, Include:

- Browser name and version

- Steps to reproduce

- Error messages (copy exact text)

- Screenshots

- JSON export of problem project (if not confidential)

## Keyboard Shortcuts Reference

### Global

- `Ctrl/Cmd + S`: Manual save

- `Ctrl/Cmd + E`: Open export menu

- `Ctrl/Cmd + H`: Toggle help modal

- `Ctrl/Cmd + /`: Toggle AI assistant

- `Ctrl/Cmd + P`: Print

- `Escape`: Close modals/panels

- `F1`: Show keyboard shortcuts

### Navigation

- `Ctrl/Cmd + 1-7`: Jump to section 1-7

- `Ctrl/Cmd + [`: Previous section

- `Ctrl/Cmd + ]`: Next section

- `Tab`: Next field

- `Shift + Tab`: Previous field

### Editing

- `Ctrl/Cmd + Z`: Undo

- `Ctrl/Cmd + Y`: Redo

- `Ctrl/Cmd + C`: Copy

- `Ctrl/Cmd + V`: Paste

- `Ctrl/Cmd + X`: Cut

- `Ctrl/Cmd + A`: Select all

### Tables

- `Enter`: Save row edit

- `Escape`: Cancel row edit

- `Delete`: Delete selected row (with confirmation)

- `Ctrl/Cmd + A`: Select all rows

- `Ctrl/Cmd + C`: Copy selected rows

### Gantt Chart

- `+`: Zoom in

- `-`: Zoom out

- `0`: Reset zoom

- `←` `→`: Scroll timeline

- `H`: Toggle high-level view

- `D`: Toggle detailed view

## Glossary

Acceptance Criteria: Standards that must be met for deliverables to be considered complete

Business Case: Justification for the project, typically including costs, benefits, and ROI

Change Control: Process for managing changes to project scope, schedule, or budget

Critical Path: Sequence of tasks that determines the project's minimum duration

Deliverable: Tangible output or result produced by the project

Gantt Chart: Visual timeline showing project phases, tasks, and dependencies

Milestone: Significant point or event in the project timeline

PID: Project Initiation Document - formal document defining the project

Risk Matrix: Visual representation plotting risks by probability and impact

Scope: Boundaries of the project - what is and isn't included

Stakeholder: Person or group with interest or influence in the project

UAT: User Acceptance Testing - validation by end users

## Appendix: Sample Projects

### Small Project Example (3-month website redesign)

- **Team**: 5 people

- **Budget**: $75K

- **Sections**: All 7 completed

- **Deliverables**: 8 major items

- **Risks**: 12 identified

- **Milestones**: 5 key dates

### Medium Project Example (6-month system integration)

- **Team**: 15 people

- **Budget**: $500K

- **Sections**: All 7 with detailed sub-sections

- **Deliverables**: 25 items

- **Risks**: 20 identified

- **Milestones**: 10 key dates

- **Gantt**: 5 phases, 40 tasks

### Large Project Example (12-month digital transformation)

- **Team**: 50+ people

- **Budget**: $2M+

- **Sections**: All 7 with extensive detail

- **Deliverables**: 50+ items

- **Risks**: 35+ identified

- **Milestones**: 20+ key dates

- **Gantt**: 8 phases, 100+ tasks

## Quick Reference Card

### Essential Workflow

- **Section 1**: Define project basics

- **Section 2**: List deliverables

- **Section 3**: Create timeline

- **Section 4**: Plan resources/budget

- **Section 5**: Identify risks

- **Section 6**: Plan communications

- **Section 7**: Define quality standards

- **Export**: Generate PDF for stakeholders

### Most Used Features

- Add table rows: "Add [Item]" button

- Edit rows: Pencil icon

- Delete rows: Trash icon

- Add Gantt phase: "Add Phase" button

- Export: "Export" dropdown in header

- Save: Auto-saves every 2 seconds

- Help: `?` icon or `F1`

### Key Principles

- Be specific and quantifiable

- Update regularly (weekly)

- Engage stakeholders throughout

- Back up data frequently

- Review before sharing

Version: 1.0.16

Last Updated: November 25, 2025

For PMO Architect Application

Support: GitHub Issues or support@pmoarchitect.com

This manual is a living document. Suggestions for improvements welcome via GitHub.